## Planning
NOCOPO DATA
PLANNING RECORD
| MDA | 539001007 FISCAL RESPONSIBILITY COMMISSION
| Budget Year | 2023
S/N | Project Code | Project Title | Project Rationale | Package Number | Lot Number | Development Partners | Budget Source | Budget Code | Budget Description | Budget Category | Budget Currency | Budget Amount | Project Estimated Currency | Project Estimated Amount | Project Category | Project Street | Project City | Nearest Landmark | Project LGA | Project State | Procurement Category | Contract type | Procurement Method | Selection Method | Appval Authority | Qualification | Review Type | Prep for Solicit Start date | Prep for Solicit End date | Is EoI applicable | Advert of EoI Start date | Advert of EoI End date | EoI Opening Event date | Eval of EoI Start Date | Eval of EoI End Date | EoI Eval Rpt Appval Start Date | EoI Eval Rpt Appval End Date | EoI Shortlist Publ Date | Invit Req Proposals Start Date | Invit Req Proposals End Date | Open of Tech Proposal Date | Tech Eval Rpt Approv Start Date | Tech Eval Rpt Approv End Date | Opening of Financial Proposal | Final Eval Rprt TF Start Date | Final Eval Rprt TF End Date | Negotiations Start Date | Negotiations End Date | Negotiations NotApplicable | Proc Entity Eval Rprt Appval Start Date | Proc Entity Eval Rprt Appval End Date | Iss of Cert of NO Eval Rprt Start Date | Iss of Cert of NO Eval Rprt End Date | Iss of Cert of NO Eval Rprt NotApplicable | Award Date | Submit of Final Rprt Start Date | Submit of Final Rprt End Date | Contract Period Start Date | Contract Period End Date | Contract Period Days | Prep of Bid Doc Advert Start Date | Prep of Bid Doc Advert End Date | Is PreQual applicable | Advert for PreQual Start Date | Advert for PreQual End Date | PreQual Opening Date | PreQual Eval Appval Start Date | PreQual Eval Appval End Date | PreQual Publish Date | Tendering Period Start Date | Tendering Period End Date | Bid Opening Date | Bid Evaluation Period Start Date | Bid Evaluation Period End Date | Proc Entity Eval Appval Start Date | Proc Entity Eval Appval End Date | Iss of Cert of NO Eval Rprt Start Date | Iss of Cert of NO Eval Rprt End Date | Contract Award Start Date | Contract Award End Date | Arrival of Goods Start Date | Arrival of Goods End Date | Substantial Completion Date | Final Acceptance Start Date | Final Acceptance End Date | Action Party Names | Action Party Designation | Action Party EMail | Action Party Phone | Champion Names | Champion Designation | Champion EMail | Champion Phone
1 | ocds-gyl66f-539001007-000001 | PURCHASE OF OFFICE FURNITURE AND FITTINGS | OPERATIONAL USE | TBS/FRC/179/2023/ | LOT 3 |  | Appropriation | ERGP23192160 | PURCHASE OF OFFICE FURNITURE AND FITTINGS | Capital |  | 28,235,981.00 | NGN | 28,235,981.00 | [6 empty] | Goods | Schedule of Delivery | Selective Tendering | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2023-06-19 | 2023-06-19 | 0 | 2023-01-05 | 2023-01-11 | Yes | 2023-01-16 | 2023-01-29 | 2023-01-29 | 2023-02-13 | 2023-02-17 | 2023-02-19 | 2023-03-06 | 2023-04-16 | 2023-08-08 | 2023-04-18 | 2023-04-24 | 2023-04-30 | 2023-05-04 | 2023-05-10 | 2023-05-23 | 2023-06-05 | 2023-06-12 | 2023-06-26 | 2023-06-27 | 2023-07-17 | 2023-10-14 | 2023-10-15 |  |  |  | '' |  |  |  | ''
2 | ocds-gyl66f-539001007-000003 | PURCHASE OF PROJECT/OPERATIONAL VEHICLES FOR THE COMMISSION | OPERATIONAL USE | TBS/FRC/182/2023 | LOT 1 |  | Appropriation | ERGP15171961 | PURCHASE OF PROJECT/OPERATIONAL VEHICLES FOR THE COMMISSION | Capital | NGN | 50,000,000.00 | NGN | 50,000,000.00 | [6 empty] | Goods | Schedule of Delivery | Selective Tendering | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2023-07-24 | 2023-08-01 | 0 | 2023-01-05 | 2023-01-11 | No | 2023-01-16 | 2023-01-29 | 2023-01-29 | 2023-02-13 | 2023-02-17 | 2023-02-19 | 2023-03-06 | 2023-04-16 | 2023-04-16 | 2023-04-18 | 2023-04-24 | 2023-04-30 | 2023-05-04 | 2023-05-10 | 2023-05-23 | 2023-07-10 | 2023-07-17 | 2023-08-08 | 2023-08-15 | 2023-08-22 | 2023-11-19 | 2023-11-20 |  |  |  | '' |  |  |  | ''
3 | ocds-gyl66f-539001007-000004 | PURCHASE OF OFFICE EQUIPMENT FOR M&E | FOR EFFECTIVE M&E ACTIVITIES | TBS/FRC/187/2023 | LOT 2B |  | Appropriation | ERGP15192158 | PURCHASE OF OFFICE EQUIPMENT FOR M&E | Capital | NGN | 9,000,000.00 | NGN | 9,000,000.00 | [6 empty] | Goods | Schedule of Delivery | Request for Quotation | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 0 | 2023-05-05 | 2023-05-11 | No | 2023-05-16 | 2023-05-29 | 2023-05-29 | 2023-06-13 | 2023-06-17 | 2023-06-19 | 2023-07-04 | 2023-08-14 | 2023-08-09 | 2023-08-16 | 2023-08-22 | 2023-08-28 | 2023-09-01 | 2023-09-07 | 2023-09-20 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
4 | ocds-gyl66f-539001007-000005 | PRINTING & PRODUCTION OF THE 2022 ANNUAL REPORT | PUBLIC AWARENESS | TBS/FRC/183/1/2023 | LOT 4 |  | Appropriation | ERGP30192156 | PRINTING & PRODUCTION OF THE 2022 ANNUAL REPORT | Capital | NGN | 9,000,000.00 | NGN | 9,000,000.00 | [6 empty] | Goods | Schedule of Delivery | Request for Quotation | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-09 | 2023-01-15 | -1 | 2023-01-20 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-02-27 | 2023-03-01 | 2023-03-03 | 2023-03-18 | 2023-04-16 | 2023-04-16 | 2023-04-18 | 2023-04-24 | 2023-05-09 | 2023-05-11 | 2023-05-17 | 2023-05-25 | 2023-05-27 | Yes | 2023-06-07 | 2023-06-11 | 2023-06-17 | 2023-06-30 |  | 2023-09-20 | 2001-01-01 | 2001-01-01 | 2023-09-21 | 2001-01-01 | 0 | 2023-05-05 | 2023-05-11 | No | 2023-01-20 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-02-23 | 2023-07-04 | 2023-08-14 | 2023-07-04 | 2023-08-16 | 2023-08-22 | 2023-08-28 | 2023-09-01 | 2023-09-07 | 2023-09-20 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
5 | ocds-gyl66f-539001007-000006 | PRINTING & PRODUCTION OF DEBT VERIFICATION REPORT (2022) FOR M&E | FOR PUBLIC USE | TBS/FRC/177/1/2023 | LOT 2B |  | Appropriation | ERGP15192158 | PRINTING & PRODUCTION OF DEBT VERIFICATION REPORT (2022) FOR M&E | Capital | NGN | 5,000,000.00 | NGN | 5,000,000.00 | [6 empty] | Goods | Schedule of Delivery | Request for Quotation | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-10 | 2023-01-16 | -1 | 2023-01-21 | 2023-02-03 | 2023-02-03 | 2023-02-18 | 2023-02-22 | 2023-02-28 | 2023-03-02 | 2023-03-04 | 2023-03-19 | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-25 | 2023-05-10 | 2023-05-12 | 2023-05-18 | 2023-05-26 | 2023-05-28 | No | 2023-06-08 | 2023-06-12 | 2023-06-18 | 2023-07-01 |  | 2023-05-10 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 0 | 2023-01-10 | 2023-01-16 | No | 2023-01-21 | 2023-02-03 | 2023-02-03 | 2023-02-18 | 2023-02-22 | 2023-02-24 | 2023-03-11 | 2023-04-21 | 2023-08-02 | 2023-04-23 | 2023-04-29 | 2023-05-05 | 2023-05-09 | 2023-05-15 | 2023-05-28 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
6 | ocds-gyl66f-539001007-000007 | PRINTING OF 2022 PROJECT VERIFICATION EXERCISE REPORT | FOR PUBLIC USE | TBS/FRC/166/1/2023 | LOT 2C |  | Appropriation | ERGP15192158 | MONITORING AND EVALUATION | Capital | NGN | 8,000,000.00 | NGN | 8,000,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-09 | 2023-01-15 | -1 | 2023-01-20 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-02-27 | 2023-03-01 | 2023-03-03 | 2023-03-18 | 2023-04-16 | 2023-04-16 | 2023-04-18 | 2023-04-24 | 2023-05-09 | 2023-05-11 | 2023-05-17 | 2023-05-25 | 2023-05-27 | No | 2023-06-07 | 2023-06-11 | 2023-06-17 | 2023-06-30 |  | 2023-09-20 | 2001-01-01 | 2001-01-01 | 2023-09-21 | 2001-01-01 | 21 | 2023-05-05 | 2023-05-11 | No | 2023-05-16 | 2023-05-29 | 2023-05-29 | 2023-06-13 | 2023-06-17 | 2023-06-19 | 2023-07-04 | 2023-08-14 | 2023-08-14 | 2023-08-16 | 2023-08-22 | 2023-08-28 | 2023-09-01 | 2023-09-07 | 2023-09-20 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
7 | ocds-gyl66f-539001007-000008 | MONITORING AND EVALUATION OF CAPITAL PROJECTS | FOR TRANSPARENCY & ACCOUNTABILITY | DME/FRC/041/VOL1 | LOT 2A |  | Appropriation | ERGP15192158 | MONITORING AND EVALUATION OF CAPITAL PROJECTS | Capital | NGN | 53,000,000.00 | NGN | 53,000,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Selective Tendering | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2023-01-09 | 2023-01-15 | -1 | 2023-01-20 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-02-27 | 2023-03-01 | 2023-03-03 | 2023-03-18 | 2023-04-16 | 2023-04-16 | 2023-04-18 | 2023-04-24 | 2023-05-09 | 2023-05-11 | 2023-05-17 | 2023-05-25 | 2023-05-27 | No | 2023-06-07 | 2023-06-11 | 2023-06-17 | 2023-06-30 |  | 2023-07-03 | 2001-01-01 | 2023-07-17 | 2023-07-10 | 2023-07-17 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
8 | ocds-gyl66f-539001007-000009 | ELECTRICITY CHARGES (UTILITIES) | OPERATIONAL USE | FRC/OFF/438/VOL :1 | LOT R1A |  | Appropriation | 22022001 | ELECTRICITY CHARGES | Recurrent | NGN | 8,000,000.00 | NGN | 8,000,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Sole Source | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-09 | 2023-01-15 | -1 | 2023-01-20 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-02-27 | 2023-03-01 | 2023-03-03 | 2023-03-18 | 2023-04-16 | 2023-04-16 | 2023-04-18 | 2023-04-24 | 2023-05-09 | 2023-05-11 | 2023-05-17 | 2023-05-25 | 2023-05-27 | No | 2023-06-07 | 2023-06-11 | 2023-06-17 | 2023-06-30 |  | 2023-07-20 | 2001-01-01 | 2023-12-31 | 2023-01-02 | 2023-12-31 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
9 | ocds-gyl66f-539001007-000010 | TELEPHONE CHARGES | OPERATIONAL USE | FRC/OFF/162/VOL: 1 | LOT R1B |  | Appropriation | 22020202 | TELEPHONE CHARGES | Recurrent | NGN | 7,200,000.00 | NGN | 7,200,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Direct Procurement | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-09 | 2023-01-15 | -1 | 2023-01-09 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-03-06 | 2023-03-01 | 2023-03-13 | 2023-03-18 | 2023-04-16 | 2023-01-04 | 2023-04-18 | 2023-04-24 | 2023-02-07 | 2023-05-11 | 2023-05-17 | 2023-05-25 | 2023-05-27 | No | 2023-06-07 | 2023-06-11 | 2023-06-17 | 2023-06-30 |  | 2023-08-07 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
10 | ocds-gyl66f-539001007-000011 | INTERNET ACCESS CHARGES | OPERATIONAL USE | DPRS/FRC/481 | LOT R1C |  | Appropriation | 22020203 | INTERNET ACCESS CHARGES | Recurrent | NGN | 6,084,000.00 | NGN | 6,084,000.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-05 | 2023-01-11 | -1 | 2023-01-16 | 2023-01-29 | 2023-01-29 | 2023-02-13 | 2023-02-17 | 2023-02-23 | 2023-02-25 | 2023-02-27 | 2023-03-14 | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-20 | 2023-05-05 | 2023-05-07 | 2023-05-13 | 2023-05-21 | 2023-05-23 | No | 2023-06-03 | 2023-06-07 | 2023-06-13 | 2023-06-26 |  | 2023-06-20 | 2001-01-01 | 2001-01-01 | 2023-01-03 | 2001-01-01 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | ''' |  |  |  | '''
11 | ocds-gyl66f-539001007-000012 | SEWAGE CHARGES | EVACUATION OF WASTE | FRC/OFF/278/VOL:1 | LOT R1D |  | Appropriation | 22020206 | SEWAGE CHARGES | Recurrent | NGN | 5,000,000.00 | NGN | 5,000,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Sole Source | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-05 | 2023-01-11 | -1 | 2023-01-16 | 2023-01-29 | 2023-01-29 | 2023-02-13 | 2023-02-17 | 2023-02-23 | 2023-02-25 | 2023-02-27 | 2023-03-14 | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-20 | 2023-05-05 | 2023-05-07 | 2023-05-13 | 2023-05-21 | 2023-05-23 | No | 2023-06-03 | 2023-06-07 | 2023-06-13 | 2023-06-26 |  | 2023-07-06 | 2023-08-08 | 2001-01-01 | 2023-07-14 | 2001-01-01 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | ''' |  |  |  | '''
12 | ocds-gyl66f-539001007-000013 | OFFICE STATIONERIES/ COMPUTER CONSUMABLES | OPERATIONAL USE | TBS/FRC/180/1 | LOT R2A |  | Appropriation | 22020301 | OFFICE STATIONERIES/ COMPUTER CONSUMABLES | Recurrent | NGN | 17,200,000.00 | NGN | 17,200,000.00 | [6 empty] | Goods | Schedule of Delivery | Request for Quotation | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2023-06-20 | 2023-07-03 | 0 | 2023-01-03 | 2023-01-09 | No | 2023-01-14 | 2023-01-27 | 2023-01-27 | 2023-02-11 | 2023-02-15 | 2023-02-17 | 2023-03-04 | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-22 | 2023-04-28 | 2023-05-02 | 2023-05-08 | 2023-05-21 | 2023-06-05 | 2023-06-13 | 2023-06-12 | 2023-06-13 | 2023-12-31 | 2024-03-29 | 2024-03-30 |  |  |  | ''' |  |  |  | '''
13 | ocds-gyl66f-539001007-000014 | NEWSPAPERS | UPDATE/INFORMATION | HPU/FRC/101/1 | LOT R2B |  | Appropriation | 22020303 | NEWSPAPERS | Recurrent | NGN | 1,440,000.00 | NGN | 1,440,000.00 | [6 empty] | Goods | Schedule of Delivery | Direct Procurement | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2023-06-20 | 2023-07-03 | 0 | 2023-01-03 | 2023-01-09 | No | 2023-01-14 | 2023-01-27 | 2023-01-27 | 2023-02-11 | 2023-02-15 | 2023-02-17 | 2023-03-04 | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-22 | 2023-04-28 | 2023-05-02 | 2023-05-08 | 2023-05-21 | 2023-06-05 | 2023-06-13 | 2023-07-10 | 2023-07-11 | 2023-10-23 | 2024-01-20 | 2024-01-21 |  |  |  | ''' |  |  |  | '''
14 | ocds-gyl66f-539001007-000015 | MAGAZINES & PERIODICALS | UPDATE/INFORMATION | FRC/OFF/241/VOL:1 | LOT R2C |  | Appropriation | 22020304 | MAGAZINES & PERIODICALS | Recurrent |  | 1,472,000.00 | NGN | 1,472,000.00 | [6 empty] | Goods | Schedule of Delivery | Repeat Procurement | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2023-09-04 | 2023-09-11 | 0 | 2023-01-09 | 2023-01-15 | No | 2023-01-20 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-02-23 | 2023-03-10 | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-04-28 | 2023-05-04 | 2023-05-08 | 2023-05-14 | 2023-05-27 | 2023-06-05 | 2023-08-20 | 2023-09-15 | 2023-09-16 | 2023-10-02 | 2023-12-30 | 2023-12-31 |  |  |  | ''' |  |  |  | '''
15 | ocds-gyl66f-539001007-000016 | PRINTING OF NON SECURITY DOCUMENTS | OPERATIONAL USE | CPA/FRC/817 | LOT R2D |  | Appropriation | 22020305 | PRINTING OF NON SECURITY DOCUMENTS | Recurrent | NGN | 5,955,728.00 | NGN | 5,955,728.00 | [6 empty] | Goods | Schedule of Delivery | Direct Labour | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2023-08-01 | 2023-08-15 | 0 | 2023-01-03 | 2023-01-09 | No | 2023-01-14 | 2023-01-27 | 2023-01-27 | 2023-02-11 | 2023-02-15 | 2023-02-17 | 2023-03-04 | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-22 | 2023-04-28 | 2023-05-02 | 2023-05-08 | 2023-05-21 | 2023-06-05 | 2023-06-06 | 2023-08-07 | 2023-08-08 | 2023-09-11 | 2023-12-09 | 2023-12-10 |  |  |  | ''' |  |  |  | '''
16 | ocds-gyl66f-539001007-000017 | PRINTING OF SECURITY DOCUMENTS | OPERATIONAL USE | CFA/FRC/803 | LOT R2E |  | Appropriation | 22020306 | PRINTING OF SECURITY DOCUMENTS | Recurrent | NGN | 5,602,743.00 | NGN | 5,602,743.00 | [6 empty] | Goods | Schedule of Delivery | Direct Labour | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2023-06-16 | 2023-07-12 | 0 | 2023-01-05 | 2023-01-11 | No | 2023-01-16 | 2023-01-29 | 2023-01-29 | 2023-02-13 | 2023-02-17 | 2023-02-19 | 2023-03-06 | 2023-04-16 | 2023-04-16 | 2023-04-18 | 2023-04-24 | 2023-04-30 | 2023-05-04 | 2023-05-10 | 2023-05-23 | 2023-06-05 | 2023-06-09 | 2023-07-19 | 1900-07-26 | 2023-08-23 | 2023-11-20 | 2023-11-21 |  |  |  | ''' |  |  |  | '''
17 | ocds-gyl66f-539001007-000018 | MAINTENANCE OF MOTOR VEHICLE/TRANSPORT EQUIPMENT | OPERATIONAL USE | FRC/OFF/87/VOL:1 | LOT R3A |  | Appropriation | 22020401 | MAINTENANCE OF MOTOR VEHICLE/TRANSPORT EQUIPMENT | Recurrent | NGN | 6,000,000.00 | NGN | 6,000,000.00 | [6 empty] | Non-Consultancy Services | Lump Sum | Repeat Procurement | Quality Based Selection(QBS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-06 | 2023-01-12 | -1 | 2023-01-17 | 2023-01-30 | 2023-01-30 | 2023-02-14 | 2023-02-18 | 2023-02-24 | 2023-02-26 | 2023-02-28 | 2023-03-15 | 2023-04-13 | 2023-04-13 | 2023-04-15 | 2023-04-21 | 2023-05-06 | 2023-05-08 | 2023-05-14 | 2023-05-22 | 2023-05-24 | No | 2023-06-04 | 2023-06-08 | 2023-06-14 | 2023-06-27 |  | 2023-07-05 | 2023-08-01 | 2023-08-15 | 2023-07-12 | 2023-07-19 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | ''' |  |  |  | '''
18 | ocds-gyl66f-539001007-000019 | MAINTENANCE OF OFFICE FURNITURE | OPERATIONAL USE | FRC/OFF/298/VOL:1 | LOT R3B |  | Appropriation | 22020402 | MAINTENANCE OF OFFICE FURNITURE | Recurrent | NGN | 3,964,728.00 | NGN | 3,964,728.00 | [6 empty] | Non-Consultancy Services | Time Based | Direct Procurement | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-09 | 2023-01-15 | 2 | 2023-01-20 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-02-27 | 2023-03-01 | 2023-03-03 | 2023-03-18 | 2023-04-16 | 2023-04-16 | 2023-04-18 | 2023-04-24 | 2023-05-09 | 2023-05-11 | 2023-05-17 | 2023-05-25 | 2023-05-27 | No | 2023-06-07 | 2023-06-11 | 2023-06-17 | 2023-06-30 |  | 2023-07-07 | 2001-01-01 | 2001-01-01 | 2023-07-14 | 2023-07-21 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | ''' |  |  |  | '''
19 | ocds-gyl66f-539001007-000020 | MAINTENANCE OF OFFICE BUILDING/ RESIDENTIAL QTRS | OPERATIONAL USE | FRC/OFF/440/VOL:1 | LOT R3C |  | Appropriation | 22020403 | MAINTENANCE OF OFFICE BUILDING/ RESIDENTIAL QTRS | Recurrent | NGN | 5,220,211.00 | NGN | 5,220,211.00 | [6 empty] | Non-Consultancy Services | Time Based | Direct Labour | Least Cost Selection(LCS) |  | Post-Qualification | Post-Review | 2023-01-05 | 2023-01-11 | 2 | 2023-01-16 | 2023-01-29 | 2023-01-29 | 2023-02-13 | 2023-02-17 | 2023-02-23 | 2023-02-25 | 2023-02-27 | 2023-03-14 | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-20 | 2023-05-05 | 2023-05-07 | 2023-05-13 | 2023-05-21 | 2023-05-23 | No | 2023-06-03 | 2023-06-07 | 2023-06-13 | 2023-06-26 |  | 2023-06-21 | 2001-01-01 | 2001-01-01 | 2023-07-03 | 2023-07-10 | 14 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
20 | ocds-gyl66f-539001007-000021 | MAINTENANCE OF OFFICE /IT EQUIPMENT | OPERATIONAL USE | FRC/OFF/298/VOL:1 | LOT R3D |  | Appropriation | 22020404 | MAINTENANCE OF OFFICE /IT EQUIPMENT | Recurrent |  | 2,492,410.00 | NGN | 2,492,410.00 | [6 empty] | Consultancy Services | Lump Sum | Request for Quotation | Quality Based Selection(QBS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-03 | 2023-01-09 | -1 | 2023-01-14 | 2023-01-27 | 2023-01-27 | 2023-02-11 | 2023-02-15 | 2023-02-21 | 2023-02-23 | 2023-02-25 | 2023-03-12 | 2023-04-10 | 2023-04-10 | 2023-04-12 | 2023-04-18 | 2023-05-03 | 2023-05-05 | 2023-05-11 | 2023-05-19 | 2023-05-21 | No | 2023-06-01 | 2023-06-05 | 2023-06-11 | 2023-06-24 |  | 2023-07-07 | 2001-01-01 | 2001-01-01 | 2023-07-14 | 2023-07-21 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
21 | ocds-gyl66f-539001007-000022 | MAINTENANCE OF PLANTS/GENERATORS | OPERATIONAL USE | FRC/OFF/401/VOL:1 | LOT R3E |  | Appropriation | 22020405 | MAINTENANCE OF PLANTS/GENERATORS | Recurrent | NGN | 4,000,000.00 | NGN | 4,000,000.00 | [6 empty] | Non-Consultancy Services | Lump Sum | Direct Procurement | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-02 | 2023-01-08 | -1 | 2023-01-13 | 2023-01-26 | 2023-01-26 | 2023-02-10 | 2023-02-14 | 2023-02-20 | 2023-02-22 | 2023-02-24 | 2023-03-11 | 2023-04-09 | 2023-04-09 | 2023-04-11 | 2023-04-17 | 2023-05-02 | 2023-05-04 | 2023-05-10 | 2023-05-18 | 2023-05-20 | No | 2023-05-31 | 2023-06-04 | 2023-06-10 | 2023-06-23 |  | 2023-07-05 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
22 | ocds-gyl66f-539001007-000023 | OTHER MAINTENANCE SERVICES | MAINTENANCE SERVICES | FRC/OFF/516/VOL:1 | LOT R3F |  | Appropriation | 2202046 | OTHER MAINTENANCE SERVICES | Recurrent | NGN | 10,124,000.00 | NGN | 10,124,000.00 | [6 empty] | Non-Consultancy Services | Lump Sum | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Permanent Secretary | Post-Qualification | Post-Review | 2023-01-02 | 2023-01-08 | 2 | 2023-01-13 | 2023-01-26 | 2023-01-26 | 2023-02-10 | 2023-02-14 | 2023-02-20 | 2023-02-22 | 2023-02-24 | 2023-03-11 | 2023-04-09 | 2023-04-09 | 2023-04-11 | 2023-04-17 | 2023-05-02 | 2023-05-04 | 2023-05-10 | 2023-05-18 | 2023-05-20 | No | 2023-05-31 | 2023-06-04 | 2023-06-10 | 2023-06-23 |  | 2023-07-07 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
23 | ocds-gyl66f-539001007-000024 | FINANCIAL CONSULTING | OPERATIONAL USE | FRC/OFF/805/VOL:11 | LOT R5A |  | Appropriation | 22020701 | FINANCIAL CONSULTING | Recurrent | NGN | 9,100,317.00 | NGN | 9,100,317.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Quality Based Selection(QBS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-03 | 2023-01-09 | -1 | 2023-01-14 | 2023-01-27 | 2023-01-27 | 2023-02-11 | 2023-02-15 | 2023-02-21 | 2023-02-23 | 2023-02-25 | 2023-03-12 | 2023-04-10 | 2023-04-10 | 2023-04-12 | 2023-04-18 | 2023-05-03 | 2023-05-05 | 2023-05-11 | 2023-05-19 | 2023-05-21 | No | 2023-06-01 | 2023-06-05 | 2023-06-11 | 2023-06-24 |  | 2023-06-20 | 2001-01-01 | 2001-01-01 | 2023-02-09 | 2001-01-01 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
24 | ocds-gyl66f-539001007-000025 | SECURITY CHARGES | SECURITY | FRC/OFF/367/VOL:1 | LOT R4A |  | Appropriation | 2202061 | SECURITY CHARGES | Recurrent | NGN | 24,500,000.00 | NGN | 24,500,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2023-01-02 | 2023-01-08 | 2 | 2023-01-13 | 2023-01-26 | 2023-01-26 | 2023-02-10 | 2023-02-14 | 2023-02-20 | 2023-02-22 | 2023-02-24 | 2023-03-11 | 2023-04-09 | 2023-04-09 | 2023-04-11 | 2023-04-17 | 2023-05-02 | 2023-05-04 | 2023-05-10 | 2023-05-18 | 2023-05-20 | No | 2023-05-31 | 2023-06-04 | 2023-06-10 | 2023-06-23 |  | 2023-07-17 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 30 | 1-01-01 | 1-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 |  |  |  | '' |  |  |  | ''
25 | ocds-gyl66f-539001007-000026 | INFORMATION COMMUNICATION CONSULTING | OPERATIONAL USE | DPRS/FRC/411 | LOT R5B |  | Appropriation | 22020702 | INFORMATION COMMUNICATION CONSULTING | Recurrent | NGN | 2,800,698.00 | NGN | 2,800,698.00 | [6 empty] | Consultancy Services | Lump Sum | Request for Quotation | Quality Based Selection(QBS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-03 | 2023-01-09 | 2 | 2023-01-14 | 2023-01-27 | 2023-01-27 | 2023-02-11 | 2023-02-15 | 2023-02-21 | 2023-02-23 | 2023-02-25 | 2023-03-12 | 2023-04-10 | 2023-04-10 | 2023-04-12 | 2023-04-18 | 2023-05-03 | 2023-05-05 | 2023-05-11 | 2023-05-19 | 2023-05-21 | No | 2023-06-01 | 2023-06-05 | 2023-06-11 | 2023-06-24 |  | 2023-08-23 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
26 | ocds-gyl66f-539001007-000027 | LAND USE CHARGES | LAND USE | FRC/OFF/71/VOL:1 | LOT R4B |  | Appropriation | 2202022 | LAND USE CHARGES | Recurrent | NGN | 25,000,000.00 | NGN | 25,000,000.00 | [6 empty] | Non-Consultancy Services | Lump Sum | Repeat Procurement | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2023-01-02 | 2023-01-08 | -1 | 2023-01-13 | 2023-01-26 | 2023-01-26 | 2023-02-10 | 2023-02-14 | 2023-02-20 | 2023-02-22 | 2023-02-24 | 2023-03-11 | 2023-04-09 | 2023-04-09 | 2023-04-11 | 2023-04-17 | 2023-05-02 | 2023-05-04 | 2023-05-10 | 2023-05-18 | 2023-05-20 | No | 2023-05-31 | 2023-06-04 | 2023-06-10 | 2023-06-23 |  | 2023-02-06 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
27 | ocds-gyl66f-539001007-000028 | CLEANING AND FUMIGATION SERVICES | ENVIRONMENTAL/CLEANING SERVICES | FRC/OFF/366/VOL:1 | LOT R4C |  | Appropriation | 22020606 | CLEANING AND FUMIGATION SERVICES | Recurrent | NGN | 28,298,868.00 | NGN | 28,298,868.00 | [6 empty] | Non-Consultancy Services | Lump Sum | Selective Tendering | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2023-01-02 | 2023-01-08 | -1 | 2023-01-13 | 2023-01-26 | 2023-01-26 | 2023-02-10 | 2023-02-14 | 2023-02-20 | 2023-02-22 | 2023-02-24 | 2023-03-11 | 2023-04-09 | 2023-04-09 | 2023-04-11 | 2023-04-17 | 2023-05-02 | 2023-05-04 | 2023-05-10 | 2023-05-18 | 2023-05-20 | No | 2023-05-31 | 2023-06-04 | 2023-06-10 | 2023-06-23 |  | 2023-06-12 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 365 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
28 | ocds-gyl66f-539001007-000029 | MEDICAL CONSULTING | HEALTH CONCERN | FRC/OFF/329/VOL:1 | LOT R5D |  | Appropriation | 22020708 | MEDICAL CONSULTING | Recurrent | NGN | 4,500,000.00 | NGN | 4,500,000.00 | [6 empty] | Consultancy Services | Time Based | Repeat Procurement | Consultant Qualification Selection(CQS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-09 | 2023-01-15 | -1 | 2023-01-20 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-02-27 | 2023-03-01 | 2023-03-03 | 2023-03-18 | 2023-04-16 | 2023-04-16 | 2023-04-18 | 2023-04-24 | 2023-05-09 | 2023-05-11 | 2023-05-17 | 2023-05-25 | 2023-05-27 | No | 2023-06-07 | 2023-06-11 | 2023-06-17 | 2023-06-30 |  | 2023-08-08 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 60 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
29 | ocds-gyl66f-539001007-000030 | LEGAL SERVICES | FOR LITIGATIONS | FRC/OFF/156/VOL:1 | LOT R5C |  | Appropriation | 22020703 | LEGAL SERVICES | Recurrent | NGN | 27,000,000.00 | NGN | 27,000,000.00 | [6 empty] | Consultancy Services | Time Based | Repeat Procurement | Consultant Qualification Selection(CQS) | Ministerial Tenders Board | Post-Qualification | Post-Review | 2023-01-04 | 2023-01-10 | 2 | 2023-01-15 | 2023-01-28 | 2023-01-28 | 2023-02-12 | 2023-02-16 | 2023-02-22 | 2023-02-24 | 2023-02-26 | 2023-03-13 | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-19 | 2023-05-04 | 2023-05-06 | 2023-05-12 | 2023-05-20 | 2023-05-22 | No | 2023-06-02 | 2023-06-06 | 2023-06-12 | 2023-06-25 |  | 2023-06-12 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 60 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
30 | ocds-gyl66f-539001007-000031 | MOTOR VEHICLE FUEL COST | OPERATIONAL USE | FRC/OFF/173/VOL:1 | LOT R6A |  | Appropriation | 22020801 | MOTOR VEHICLE FUEL COST | Recurrent | NGN | 10,400,000.00 | NGN | 10,400,000.00 | [6 empty] | Goods | Schedule of Delivery | Direct Procurement | Lowest Evaluated Responsive Bid | Accounting Officer-Permanent Secretary | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2023-08-21 | 2023-08-28 | 0 | 2023-01-03 | 2023-01-09 | No | 2023-01-14 | 2023-01-27 | 2023-01-27 | 2023-02-11 | 2023-02-15 | 2023-02-17 | 2023-03-04 | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-22 | 2023-04-28 | 2023-05-02 | 2023-05-08 | 2023-05-21 | 2023-08-07 | 2023-08-14 | 2023-09-04 | 2023-09-05 | 2023-09-11 | 2023-12-09 | 2023-12-10 |  |  |  | '' |  |  |  | ''
31 | ocds-gyl66f-539001007-000032 | PLANT/ GENERATOR FUEL COST | OPERATIONAL USE | FRC/OFF/337/VOL:1 | LOT R6B |  | Appropriation | 22020803 | PLANT/ GENERATOR FUEL COST | Recurrent | NGN | 10,800,000.00 | NGN | 10,800,000.00 | [6 empty] | Goods | Schedule of Delivery | Direct Labour | Lowest Evaluated Responsive Bid | Accounting Officer-Permanent Secretary | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2023-06-12 | 2023-06-19 | 0 | 2023-01-03 | 2023-01-09 | No | 2023-01-14 | 2023-01-27 | 2023-01-27 | 2023-02-11 | 2023-02-15 | 2023-02-17 | 2023-03-04 | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-22 | 2023-04-28 | 2023-05-02 | 2023-05-08 | 2023-05-21 | 2023-05-29 | 2023-06-05 | 2023-06-26 | 2023-06-27 | 2023-08-07 | 2023-11-04 | 2023-11-05 |  |  |  | '' |  |  |  | ''
32 | ocds-gyl66f-539001007-000033 | SATELLITE BROADCASTING ACCESS CHARGES | OPERATIONAL USE | TBS/FRC/177/1 | LOT RIC |  | Appropriation | 22020204 | SATELLITE BROADCASTING ACCESS CHARGES | Recurrent | NGN | 1,300,000.00 | NGN | 1,300,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Direct Procurement | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2023-01-02 | 2023-01-08 | -1 | 2023-01-13 | 2023-01-26 | 2023-01-26 | 2023-02-10 | 2023-02-14 | 2023-02-20 | 2023-02-22 | 2023-02-24 | 2023-03-11 | 2023-04-09 | 2023-04-09 | 2023-04-11 | 2023-04-17 | 2023-05-02 | 2023-05-04 | 2023-05-10 | 2023-05-18 | 2023-05-20 | No | 2023-05-31 | 2023-06-04 | 2023-06-10 | 2023-06-23 |  | 2023-07-04 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
33 | ocds-gyl66f-539001007-000034 | RESEARCH AND DEVELOPMENT | FISCAL AND FINANCIAL STUDIES | TBS/FRC/174/1 | LOT 4A |  | Appropriation | ERGP30192156 | RESEARCH AND DEVELOPMENT | Capital | NGN | 26,000,000.00 | NGN | 26,000,000.00 | [6 empty] | Consultancy Services | Time Based | Selective Tendering | Quality & Cost Based Selection(QCBS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2023-01-09 | 2023-01-15 | 2 | 2023-01-20 | 2023-02-02 | 2023-02-02 | 2023-02-17 | 2023-02-21 | 2023-02-27 | 2023-03-01 | 2023-03-03 | 2023-03-18 | 2023-04-16 | 2023-04-16 | 2023-04-18 | 2023-04-24 | 2023-05-09 | 2023-05-11 | 2023-05-17 | 2023-05-25 | 2023-05-27 | No | 2023-06-07 | 2023-06-11 | 2023-06-17 | 2023-06-30 |  | 2023-07-10 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 60 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''

## Records
NOCOPO DATA
AWARD RECORD
| MDA | 539001007 FISCAL RESPONSIBILITY COMMISSION
S/N | Tender ID | Planning | Tender Title | Tender Description | Tender Status | Actual Procurement Method | Procurement Method Rationale | Actual Selection Method | Actual Approval Authority | Submission Method | Submission method details | Actual Tendering Period Start Date | Actual Tendering Period End Date | Advertisement Media | Any Enquiries | Eligibility Criteria | Actual Bid Opening | Number of Tenderers | Names of Tenders | Actual Bid Evaluation Period Start Date | Actual Bid Evaluation Period End Date | Actual Procuring Entity Evaluation Approval Start Date | Actual Procuring Entity Evaluation Approval End Date | Certificate Of No Objection Start Date | Certificate Of No Objection End Date | Certificate Of Not Applicable | Project Code | Award Title | Award Description | Award Status | Award Date | Tender | Contractor Awarded Name | BPP Number | To lowest priced tenderer | Justification for award | Contract Currency | Contract Value | Project Code | Contract Title | Contract Description | Contract Status | Award | Date Contract Signed | Actual Contract Period Start Day | Actual Contract Period End Day | Project Code | Contract | Date of Evaluation | AP Curency | Amount Paid as at Date | Project Status | Percentage Completion | Final Cost Curency | Final Cost | Any Contract Variation | Variation Amount Currency | Variation Amount | BPP Ref No for Approval of Variation | Currency | Total Revised Estimated Contract Amount
1 | ocds-gyl66f-539001007-000003 | ocds-gyl66f-539001007-000003 - PURCHASE OF PROJECT/OPERATIONAL VEHICLES FOR THE COMMISSION | PURCHASE OF MOTOR VEHICLE (2023) | PROCUREMENT OF MOTOR VEHICLE | Complete | Selective Tendering | TO SAVE COST AND TIME | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Written | TENDERS DOCUMENT HAVE BEEN SUBMITTED IN THE SECRETARY TENDERS BOARD OFFICE | Actual_Tendering_Period_Start_Date__FEx | 1-01-01 |  | No |  | 2024-10-01 | 1 |  | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | 1-01-01 | Yes | ocds-gyl66f-539001007-000003-2023-A00004 | SUPPLY OF (1) ONE TOYOTA HIACE HIGH ROOF BUS | SUPPLY OF (1) ONE TOYOTA HIACE HIGH ROOF BUS | Active | 2023-10-10 | ocds-gyl66f-539001007-000003 | KOJO MOTORS, MAGNOS AUTOMOBILE LTD,KAURA MOTORS, COPIOUS AUTOMOBILE SYSTEMS, LANRE SHITTU AND MATRIX AUTOMOBILE SYSTEMS |  | No |  | NGN | 49,710,982.00 | ocds-gyl66f-539001007-000003-2023-C00003 | SUPPLY OF (1) ONE ONE TOYOTA HIACE HIGH ROOF | SUPPLY OF (1) ONE ONE TOYOTA HIACE HIGH ROOF | Active | ocds-gyl66f-539001007-000003-2023-A00004 | 2023-10-13 | 1-01-01 | 1-01-01 | ocds-gyl66f-539001007-000003-2023-C00003 | ocds-gyl66f-539001007-000003-2023-C00003 | 1-01-01 | NGN | 49,710,982.00 | Completed | 100 | NGN | 49,710,982.00 | No | NGN | 0.00 |  | NGN | 0.00
2 | ocds-gyl66f-539001007-000001 | ocds-gyl66f-539001007-000001 - PURCHASE OF OFFICE FURNITURE AND FITTINGS | PURCHASE OF OFFICE FURNITURE AND FITTINGS | PURCHASE OF OFFICE FURNITURE AND FITTINGS | Complete | National Shopping | TO SAVE COST AND TIME | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Written | TENDERS DOCUMENT HAVE BEEN SUBMITTED IN THE SECRETARY TENDERS BOARD OFFICE |  | 2001-01-01 |  | No |  | 2001-01-01 | 4 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | No | ocds-gyl66f-539001007-000001-2023-A00006 | SUPPLY AND INSTALLATION OF FURNITURE/FITTINGS | SUPPLY AND INSTALLATION OF FURNITURE/FITTINGS | Active | 2023-08-21 | ocds-gyl66f-539001007-000001 | BUCHRIS INTERNATIONAL RESOURCE LTD, SMART-B-LYNO NIG. LTD ANDEMMANUELLA CASTELLO ENTERPRISE |  | No |  | NGN | 5,777,500.00 | ocds-gyl66f-539001007-000001-2023-C00005 | SUPPLY AND INSTALLATION OF FURNITURE/FITTINGS | SUPPLY AND INSTALLATION OF FURNITURE/FITTINGS | Active | ocds-gyl66f-539001007-000001-2023-A00006 | 2023-11-10 | 1-01-01 | 1-01-01 | ocds-gyl66f-539001007-000001-2023-C00005 | ocds-gyl66f-539001007-000001-2023-C00005 | 1-01-01 | NGN | 5,775,500.00 | Completed | 100 | NGN | 5,777,500.00 | No | NGN | 0.00 |  | NGN | 0.00