## Planning
NOCOPO DATA
PLANNING RECORD
| MDA | 539001007 FISCAL RESPONSIBILITY COMMISSION
| Budget Year | 2024
S/N | Project Code | Project Title | Project Rationale | Package Number | Lot Number | Development Partners | Budget Source | Budget Code | Budget Description | Budget Category | Budget Currency | Budget Amount | Project Estimated Currency | Project Estimated Amount | Project Category | Project Street | Project City | Nearest Landmark | Project LGA | Project State | Procurement Category | Contract type | Procurement Method | Selection Method | Appval Authority | Qualification | Review Type | Prep for Solicit Start date | Prep for Solicit End date | Is EoI applicable | Advert of EoI Start date | Advert of EoI End date | EoI Opening Event date | Eval of EoI Start Date | Eval of EoI End Date | EoI Eval Rpt Appval Start Date | EoI Eval Rpt Appval End Date | EoI Shortlist Publ Date | Invit Req Proposals Start Date | Invit Req Proposals End Date | Open of Tech Proposal Date | Tech Eval Rpt Approv Start Date | Tech Eval Rpt Approv End Date | Opening of Financial Proposal | Final Eval Rprt TF Start Date | Final Eval Rprt TF End Date | Negotiations Start Date | Negotiations End Date | Negotiations NotApplicable | Proc Entity Eval Rprt Appval Start Date | Proc Entity Eval Rprt Appval End Date | Iss of Cert of NO Eval Rprt Start Date | Iss of Cert of NO Eval Rprt End Date | Iss of Cert of NO Eval Rprt NotApplicable | Award Date | Submit of Final Rprt Start Date | Submit of Final Rprt End Date | Contract Period Start Date | Contract Period End Date | Contract Period Days | Prep of Bid Doc Advert Start Date | Prep of Bid Doc Advert End Date | Is PreQual applicable | Advert for PreQual Start Date | Advert for PreQual End Date | PreQual Opening Date | PreQual Eval Appval Start Date | PreQual Eval Appval End Date | PreQual Publish Date | Tendering Period Start Date | Tendering Period End Date | Bid Opening Date | Bid Evaluation Period Start Date | Bid Evaluation Period End Date | Proc Entity Eval Appval Start Date | Proc Entity Eval Appval End Date | Iss of Cert of NO Eval Rprt Start Date | Iss of Cert of NO Eval Rprt End Date | Contract Award Start Date | Contract Award End Date | Arrival of Goods Start Date | Arrival of Goods End Date | Substantial Completion Date | Final Acceptance Start Date | Final Acceptance End Date | Action Party Names | Action Party Designation | Action Party EMail | Action Party Phone | Champion Names | Champion Designation | Champion EMail | Champion Phone
1 | ocds-gyl66f-539001007-000035 | RESEARCH AND DEVELOPMENT | CAPACITY BUILDING & HUMAN DEVELOPMENT | TBS/FRC/200/I/2024 | 01A |  | Appropriation | ERGP15211545 | RESEARCH AND DEVELOPMENT OF MTEF ANALYSIS TEMPLATE, CAPACITY BUILDING AND CONSULTANCY | Capital |  | 9,700,000.00 | NGN | 9,700,000.00 | [6 empty] | Consultancy Services |  |  |  |  | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | -1 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | No | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-06-03 | 2001-06-29 | 2024-07-02 | 2024-06-12 | 2024-06-19 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | ' |  |  |  | '
2 | ocds-gyl66f-539001007-000036 | MONITORING AND EVALUATION OF OF FEDERAL GOVERNMENT CAPITAL PROJECTS ACR0SS THE 36 STATES | TO ENSURE TRANSPARENCY,ACCOUNTABILITY, VALUE FOR MONEY AND CAPACITY BUILDING | FRC/OFF/241/VOL:1 | 002A |  | Appropriation | ERGP15211548 | MONITORING AND EVALUATION OF OF FEDERAL GOVERNMENT CAPITAL PROJECTS ACROSS THE 36 STATES, REVENUE MO | Capital | NGN | 41,000,000.00 | NGN | 41,000,000.00 | [6 empty] | Consultancy Services | Lump Sum | Selective Tendering | Least Cost Selection(LCS) | Ministerial Tenders Board | Pre-Qualification | Prior-Review | 2024-01-10 | 2024-01-16 | -1 | 2024-01-21 | 2024-02-03 | 2024-02-03 | 2024-02-18 | 2024-02-22 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-18 | 2024-04-16 | 2024-04-16 | 2024-04-18 | 2024-04-24 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-25 | 2024-05-27 | No | 2024-06-07 | 2024-06-11 | 2024-06-17 | 2024-06-30 |  | 2024-06-28 | 2024-08-13 | 2024-07-24 | 2024-07-14 | 2024-07-24 | 7 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
3 | ocds-gyl66f-539001007-000037 | PURCHASE OF CHAIRS, TABLES AND OTHERS FURNITURE AND FITTINGS | FOR CONDUCIVE ENVIRONMENT AND PRODUCTIVITY | TBS/FRC/190/1/2024 | 3 |  | Appropriation | ERGP23211547 | PURCHASE OF CHAIRS, TABLES AND OTHERS FURNITURE AND FITTINGS | Capital |  | 36,080,051.00 | NGN | 36,080,051.00 | [6 empty] | Goods | Rates/% | Selective Tendering | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-07 | 2024-06-14 | 0 | 2024-01-02 | 2024-01-08 | No | 2024-01-13 | 2024-01-26 | 2024-01-26 | 2024-02-10 | 2024-02-14 | 2024-02-16 | 2024-03-02 | 2024-04-12 | 2024-04-12 | 2024-04-14 | 2024-04-20 | 2024-04-26 | 2024-04-30 | 2024-05-06 | 2024-05-19 | 2024-05-01 | 2024-05-30 | 2024-06-21 | 2024-06-22 | 2024-08-02 | 2024-10-30 | 2024-10-31 |  |  |  | '' |  |  |  | ''
4 | ocds-gyl66f-539001007-000038 | RETREAT ON FISCAL RESPONSIBILITY OF SUB-NATIONALS AND CIVIL SOCIETIES | FOR AWARENESS AND SENSITIZATION | TBS/FRC/191/1/2024 | 4 |  | Appropriation | ERGP20241601 | RETREAT ON FISCAL RESPONSIBILITY OF SUB-NATIONALS AND CIVIL SOCIETIES | Capital |  | 99,185,304.00 | NGN | 99,185,304.00 | [6 empty] | Consultancy Services | Time Based | Selective Tendering | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | -1 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | No | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-06-05 | 2024-07-01 | 2024-06-11 | 2024-06-12 | 2024-06-11 | 7 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
5 | ocds-gyl66f-539001007-000039 | financial accountability retreat of sub-national and civil societies | FOR AWARENESS AND SENSITIZATION | TB/FRC/192/1/2024 | 5 |  | Appropriation | ERGP20241602 | FINANCIAL ACCOUNTABILITY RETREAT OFSUB-NATIONALS AND CIVIL SOCIETIES | Capital | NGN | 99,185,304.00 | NGN | 99,185,304.00 | [6 empty] | Consultancy Services | Time Based | Selective Tendering | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | 2 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | Yes | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-06-03 | 2024-06-17 | 2024-06-13 | 2024-06-10 | 2024-06-13 | 5 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
6 | ocds-gyl66f-539001007-000040 | PROVISION OF SOLAR-POWERED BOREHOLES IN AFIKPO AND EDDA FEDERAL CONSTITUENCY | TO PROVIDE PORTABLE WATER | TB/FRC/194/1/2024 | 6 |  | Appropriation | ERGP20242018 | PROVISION OF SOLAR-POWERED BOREHOLES IN AFIKPO AND EDDA FEDERAL CONSTITUENCY | Capital | NGN | 100,000,000.00 | NGN | 100,000,000.00 | [6 empty] | Works | BOQ | Selective Tendering | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-07-11 | 2024-07-16 | 0 | 2024-01-01 | 2024-01-07 | No | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-15 | 2024-03-01 | 2024-04-11 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-25 | 2024-04-29 | 2024-05-05 | 2024-05-18 | 2024-05-27 | 2024-07-04 | 2024-07-23 | 2024-07-24 | 2024-05-07 | 2024-08-04 | 2024-08-05 |  |  |  | '' |  |  |  | ''
7 | ocds-gyl66f-539001007-000041 | AWARENESS AND SENSITIZATION PROGRAM ON TRANSPARENCY AND ACCOUNTABILITY FOR SUB-NATIONALS IN NORTH CENTRAL STATES IN NIGERIA | FOR AWARENESS AND SENSITIZATION | TBS/FRC/193/1/2024 | 0O7 |  | Appropriation | ERGP20247339 | AWARENESS AND SENSITIZATION PROGRAM | Capital | NGN | 100,000,000.00 | NGN | 100,000,000.00 | [6 empty] | Consultancy Services | Time Based | Selective Tendering | Least Cost Selection(LCS) | Ministerial Tenders Board | Pre-Qualification | Prior-Review | 2024-01-01 | 2024-01-07 | 2 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | No | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-06-03 | 2024-06-24 | 2024-07-01 | 2024-06-10 | 2024-06-17 | 5 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
8 | ocds-gyl66f-539001007-000042 | REVENUE MONITORING | FOR REVENUE EFFICIENCY | FRC/M&E/150/1 | 002B |  | Appropriation | ERGP15211548 | REVENUE MONITORING | Capital | NGN | 20,000,000.00 | NGN | 20,000,000.00 | [6 empty] | Consultancy Services |  | Selective Tendering |  |  | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | -1 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | No | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-06-10 | 2024-06-18 | 2024-06-25 | 2001-06-18 | 2024-06-25 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
9 | ocds-gyl66f-539001007-000043 | DEBT VERIFICATION | FOR EFFECTIVE IMPLIMENTATION | TBS/FRC/202/2024 | 002C |  | Appropriation | ERGP15211548 | DEBT VERIFICATION | Capital | NGN | 31,500,000.00 | NGN | 31,500,000.00 | [6 empty] | Consultancy Services | Time Based | Selective Tendering | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | -1 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | No | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-06-04 | 2024-07-16 | 2024-07-03 | 2024-06-26 | 2024-07-03 | 5 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
10 | ocds-gyl66f-539001007-000044 | CAPACITY BUILDING | FOR PRODUCTIVITY | FRC/OFF/200/2024 | 002D |  | Appropriation | ERGP15211548 | CAPITAL BUILDING | Capital | NGN | 27,000,000.00 | NGN | 27,000,000.00 | [6 empty] | Consultancy Services | Time Based | Selective Tendering | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | 1 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | No | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-06-04 | 2024-09-02 | 2024-06-25 | 2024-06-18 | 2024-06-25 | 5 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
11 | ocds-gyl66f-539001007-000045 | CONSULTANCY | FOR EFFICIENCY | FRC/0FF/201/2024 | 002E |  | Appropriation | ERGP15211548 | Consultancy | Capital | NGN | 9,500,000.00 | NGN | 9,500,000.00 | [6 empty] | Consultancy Services |  | Selective Tendering |  |  | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | 2 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | No | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-06-18 | 2024-08-06 | 2024-07-16 | 2024-06-25 | 2024-07-16 | 300 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
12 | ocds-gyl66f-539001007-000046 | PRINTING OF PROJECT VERIFICATION REPORT | FOR STAKEHOLDERS USE | FRC/M&E/202/2024 | 002F |  | Appropriation | ERGP15211548 | PRINTING OF PROJECT VERIFICATION REPORT | Capital | NGN | 7,000,000.00 | NGN | 7,000,000.00 | [6 empty] | Goods | Schedule of Delivery | Selective Tendering | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | No | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-11 | 2024-06-18 | 0 | 2024-01-01 | 2024-01-07 | No | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-15 | 2024-03-01 | 2024-04-11 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-25 | 2024-04-29 | 2024-05-05 | 2024-05-18 | 2024-05-27 | 2024-06-03 | 2024-06-25 | 2024-06-26 | 2024-07-16 | 2024-10-13 | 2024-10-14 |  |  |  | '' |  |  |  | ''
13 | ocds-gyl66f-539001007-000047 | PRINTING OF DEBT MONITORING REPORT | FOR STAKEHOLDERS USE | FRC/P&S/197/2024 | 002G |  | Appropriation | ERGP15211548 | PRINTING OF DEBT MONITORING REPORT | Capital | NGN | 7,000,000.00 | NGN | 7,000,000.00 | [6 empty] | Goods | Schedule of Delivery | Request for Quotation | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-13 | 2024-06-20 | 0 | 2024-01-01 | 2024-01-07 | No | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-15 | 2024-03-01 | 2024-04-11 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-25 | 2024-04-29 | 2024-05-05 | 2024-05-18 | 2024-05-28 | 2024-06-06 | 2024-06-27 | 2024-07-09 | 2024-09-03 | 2024-12-01 | 2024-12-02 |  |  |  | ' |  |  |  | '
14 | ocds-gyl66f-539001007-000048 | BANK VERIFICATION | FOR TRANSPARENCY AND ACCOUNTABILITY IN FINANCIAL MANAGEMENT | FRC/P&S/203/2024 | 002H |  | Appropriation | ERGP15211548 | BANK VERIFICATION | Capital | NGN | 7,000,000.00 | NGN | 7,000,000.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | -1 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | No | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-06-04 | 2024-08-05 | 2024-06-17 | 2024-06-10 | 2024-06-17 | 7 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
15 | ocds-gyl66f-539001007-000049 | PRINTING OF 2023 ANNUAL REPORT | FOR STAKEHOLDERS USES | TB/FRC/189/2024 | 001D |  | Appropriation | ERGP15211545 | PRINTING OF 2023 ANNUAL REPORT | Capital | NGN | 9,500,000.00 | NGN | 9,500,000.00 | [6 empty] | Goods | Schedule of Delivery | Request for Quotation | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-17 | 2024-07-24 | 0 | 2024-01-09 | 2024-01-15 |  | 2024-01-20 | 2024-02-02 | 2024-02-02 | 2024-02-17 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-19 | 2024-04-19 | 2024-04-21 | 2024-04-27 | 2024-05-03 | 2024-05-07 | 2024-05-13 | 2024-05-26 | 2024-06-03 | 2024-06-10 | 2024-08-01 | 2024-08-02 | 2024-08-20 | 2024-11-17 | 2024-11-18 |  |  |  | '' |  |  |  | ''
16 | ocds-gyl66f-539001007-000050 | PRINTING OF IMF REPORT | FOR STAKEHOLDERS USE | TB/FRC/206/2024 | 001E |  | Appropriation | ERGP15211545 | PRINTING OF IMF REPORT | Capital |  | 7,500,000.00 | NGN | 7,500,000.00 | [6 empty] | Goods | Schedule of Delivery | Request for Quotation | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-12 | 2024-06-20 | 0 | 2024-01-04 | 2024-01-10 | No | 2024-01-15 | 2024-01-28 | 2024-01-28 | 2024-02-12 | 2024-02-16 | 2024-02-18 | 2024-03-04 | 2024-04-14 | 2024-04-14 | 2024-04-16 | 2024-04-22 | 2024-04-28 | 2024-05-02 | 2024-05-08 | 2024-05-21 | 2024-05-28 | 2024-06-05 | 2024-06-27 | 2024-06-28 | 2024-07-15 | 2024-10-12 | 2024-10-13 |  |  |  | '' |  |  |  | ''
17 | ocds-gyl66f-539001007-000051 | CAPACITY BUILDING FOR PLANNING, RESEARCH AND STATISTICS STAFF | FOR PRODUCTIVITY | FRC/OFF/241/VOL:1 | 001B |  | Appropriation | ERGP152115 | CAPACITY BUILDING FOR PLANNING, RESEARCH AND STATISTICS STAFF | Capital | NGN | 23,500,000.00 | NGN | 23,500,000.00 | [6 empty] | Consultancy Services |  |  |  |  | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | -1 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | Yes | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-07-01 | 2024-08-26 | 2024-07-30 | 2024-07-16 | 2024-07-30 | 14 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | ' |  |  |  | '
18 | ocds-gyl66f-539001007-000052 | CONSULTANCY ON MTEF ANALYSIS TEMPLATE | FOR EFFICIENCY AND EFFECTIVELY | FRC/OFF/241/VOL:1 | 001C |  | Appropriation | ERGP15211545 | CONSULTANCY ON MTEF ANALYSIS TEMPLATE | Capital |  | 9,800,000.00 | NGN | 9,800,000.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-02-12 | 2024-02-18 | -1 | 2024-02-23 | 2024-03-07 | 2024-03-07 | 2024-03-22 | 2024-03-26 | 2024-04-01 | 2024-04-03 | 2024-04-05 | 2024-04-20 | 2024-05-19 | 2024-05-19 | 2024-05-21 | 2024-05-27 | 2024-06-11 | 2024-06-13 | 2024-06-19 | 2024-06-27 | 2024-06-29 | No | 2024-07-10 | 2024-07-14 | 2024-07-20 | 2024-08-02 |  | 2024-07-22 | 2024-09-02 | 2024-08-10 | 2024-08-03 | 2024-08-10 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
19 | ocds-gyl66f-539001007-000053 | ELECTRICITY CHARGES | FOR LIGHT | FRC/OFF/438/VOL | RA 201 |  | Appropriation | 22020201 | ELECTRICITY CHARGES | Recurrent |  | 0.00 | NGN | 8,400,000.00 | [6 empty] | Non-Consultancy Services |  |  |  |  | Post-Qualification | Post-Review | 2024-01-01 | 2024-01-07 | 2 | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-19 | 2024-02-21 | 2024-02-23 | 2024-03-09 | 2024-04-07 | 2024-04-07 | 2024-04-09 | 2024-04-15 | 2024-04-30 | 2024-05-02 | 2024-05-08 | 2024-05-16 | 2024-05-18 | Yes | 2024-05-29 | 2024-06-02 | 2024-06-08 | 2024-06-21 |  | 2024-07-02 | 2024-09-10 | 2024-07-30 | 2024-07-16 | 2024-07-30 | 360 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | ' |  |  |  | '
20 | ocds-gyl66f-539001007-000054 | TELEPHONE CHARGES | FOR COMMUNICATION | FRC/OFF/162/VOL | RA202 |  | Appropriation | 22020202 | TELEPHONE CHARGES | Recurrent |  | 7,200,000.00 | NGN | 7,200,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-01-02 | 2024-01-08 | 2 | 2024-01-13 | 2024-01-26 | 2024-01-26 | 2024-02-10 | 2024-02-14 | 2024-02-20 | 2024-02-22 | 2024-02-24 | 2024-03-10 | 2024-04-08 | 2024-04-08 | 2024-04-10 | 2024-04-16 | 2024-05-01 | 2024-05-03 | 2024-05-09 | 2024-05-17 | 2024-05-19 | Yes | 2024-05-30 | 2024-06-03 | 2024-06-09 | 2024-06-22 |  | 2024-07-08 | 2024-08-06 | 2024-07-22 | 2024-07-15 | 2024-07-22 | 366 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
21 | ocds-gyl66f-539001007-000055 | INTERNET ACCESS CHARGES | FOR INTERNET ACCESSESSBILITY | DPRS/FRC/481 | RA203 |  | Appropriation | 22020203 | INTERNET ACCEESS | Recurrent |  | 8,000,000.00 | NGN | 8,000,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-02-05 | 2024-02-11 | -1 | 2024-02-16 | 2024-02-29 | 2024-02-29 | 2024-03-15 | 2024-03-19 | 2024-03-25 | 2024-03-27 | 2024-03-29 | 2024-04-13 | 2024-05-12 | 2024-05-12 | 2024-05-14 | 2024-05-20 | 2024-06-04 | 2024-06-06 | 2024-06-12 | 2024-06-20 | 2024-06-22 | Yes | 2024-07-03 | 2024-07-07 | 2024-07-13 | 2024-07-26 |  | 2024-07-15 | 2024-08-14 | 2024-07-30 | 2024-07-22 | 2024-07-30 | 366 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
22 | ocds-gyl66f-539001007-000056 | SATELLITE BROADCASTING ACCESS CHARGES | ACCESSESSBILITY | FRC/OFF/431/VOL | RA204 |  | Appropriation | 22020204 | SATELLITE BROADCASTING ACCESS CHARGES | Recurrent |  | 1,500,000.00 | NGN | 1,500,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Request for Quotation | Single Source Selection(SSS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-02-05 | 2024-02-11 | 2 | 2024-02-16 | 2024-02-29 | 2024-02-29 | 2024-03-15 | 2024-03-19 | 2024-03-25 | 2024-03-27 | 2024-03-29 | 2024-04-13 | 2024-05-12 | 2024-05-12 | 2024-05-14 | 2024-05-20 | 2024-06-04 | 2024-06-06 | 2024-06-12 | 2024-06-20 | 2024-06-22 | Yes | 2024-07-03 | 2024-07-07 | 2024-07-13 | 2024-07-26 |  | 2024-07-15 | 2024-08-20 | 2024-08-05 | 2024-07-30 | 2024-08-05 | 366 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
23 | ocds-gyl66f-539001007-000057 | SEWERAGE CHARGES | FOR CLEANESS | FRC/OFF/431/VOL | RA206 |  | Appropriation | 22020206 | SEWERAGE CHARGES | Recurrent |  | 2,000,000.00 | NGN | 2,000,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Request for Quotation | Single Source Selection(SSS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-02-01 | 2024-02-07 | 2 | 2024-02-12 | 2024-02-25 | 2024-02-25 | 2024-03-11 | 2024-03-15 | 2024-03-21 | 2024-03-23 | 2024-03-25 | 2024-04-09 | 2024-05-08 | 2024-05-08 | 2024-05-10 | 2024-05-16 | 2024-05-31 | 2024-06-02 | 2024-06-08 | 2024-06-16 | 2024-06-18 | No | 2024-06-29 | 2024-07-03 | 2024-07-09 | 2024-07-22 |  | 2024-07-30 | 2024-09-03 | 2024-08-14 | 2024-08-07 | 2024-08-14 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
24 | ocds-gyl66f-539001007-000058 | OFFICE STATIONERIES/COMPUTER CONSUMABLES | FOR OFFICE USES | TBS/FRC/198/I/2024 | RB301 |  | Appropriation | 22020301 | OFFICE STATIONERIES/COMPUTER CONSUMABLE | Recurrent |  | 18,280,000.00 | NGN | 18,280,000.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-02 | 2024-01-08 | -1 | 2024-01-13 | 2024-01-26 | 2024-01-26 | 2024-02-10 | 2024-02-14 | 2024-02-20 | 2024-02-22 | 2024-02-24 | 2024-03-10 | 2024-04-08 | 2024-04-08 | 2024-04-10 | 2024-04-16 | 2024-05-01 | 2024-05-03 | 2024-05-09 | 2024-05-17 | 2024-05-19 | Yes | 2024-05-30 | 2024-06-03 | 2024-06-09 | 2024-06-22 |  | 2024-06-28 | 2024-09-16 | 2024-07-16 | 2024-07-08 | 2024-07-16 | 14 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
25 | ocds-gyl66f-539001007-000059 | NEWSPAPERS | FOR UP DATE | FRC/SC/241/VOL:1 | RB303 |  | Appropriation | 22020303 | NEWSPAPERS | Recurrent |  | 1,680,000.00 | NGN | 1,680,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Direct Labour | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-01-02 | 2024-01-08 | -1 | 2024-01-13 | 2024-01-26 | 2024-01-26 | 2024-02-10 | 2024-02-14 | 2024-02-20 | 2024-02-22 | 2024-02-24 | 2024-03-10 | 2024-04-08 | 2024-04-08 | 2024-04-10 | 2024-04-16 | 2024-05-01 | 2024-05-03 | 2024-05-09 | 2024-05-17 | 2024-05-19 | Yes | 2024-05-30 | 2024-06-03 | 2024-06-09 | 2024-06-22 |  | 2024-06-10 | 2024-08-06 | 2024-06-24 | 2024-06-17 | 2024-06-24 | 366 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
26 | ocds-gyl66f-539001007-000060 | MAGAZINES AND PERIODICALS | FOR INFORMATION | FRC/OFF/247/VOL:1 | RB304 |  | Appropriation | 22020304 | MAGAZINES AND PERIODICALS | Recurrent |  | 1,472,000.00 | NGN | 1,472,000.00 | [6 empty] | Goods | Schedule of Delivery | Request for Quotation | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2024-01-19 | 2024-02-01 | 2024-02-01 | 2024-02-16 | 2024-02-20 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-05-23 | 2024-05-25 | Yes | 2001-01-01 | 2001-01-01 | 2024-06-15 | 2024-06-28 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-10 | 2024-07-09 | 0 | 2024-01-03 | 2024-01-09 | No | 2024-01-14 | 2024-01-27 | 2024-01-27 | 2024-02-11 | 2024-02-15 | 2024-02-17 | 2024-03-03 | 2024-04-13 | 2024-04-13 | 2024-04-15 | 2024-04-21 | 2024-04-27 | 2024-05-01 | 2024-05-07 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-07-15 | 2024-07-16 | 2024-07-23 | 2024-10-20 | 2024-10-21 |  |  |  | '' |  |  |  | ''
27 | ocds-gyl66f-539001007-000061 | PRINTING OF NON SECURITY DOCUMENT | FOR SMOOTH WORKING ACTIVITIES | FRC/OFF/441/VOL:1 | RB305 |  | Appropriation | 22020305 | PRINTING OF NON SECURITY DOCUMENT | Recurrent |  | 7,000,000.00 | NGN | 7,000,000.00 | [6 empty] | Goods | Schedule of Delivery | Repeat Procurement | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-13 | 2024-06-20 | 0 | 2024-01-04 | 2024-01-10 |  | 2024-01-15 | 2024-01-28 | 2024-01-28 | 2024-02-12 | 2024-02-16 | 2024-02-18 | 2024-03-04 | 2024-04-14 | 2024-04-14 | 2024-04-16 | 2024-04-22 | 2024-04-28 | 2024-05-02 | 2024-05-08 | 2024-05-21 | 2024-05-28 | 2024-06-06 | 2024-06-27 | 2024-06-28 | 2024-09-17 | 2024-12-15 | 2024-12-16 |  |  |  | '' |  |  |  | ''
28 | ocds-gyl66f-539001007-000062 | PRINTING OF SECURITY DOCUMENT | FOR SMOOTH WORKING ACTIVITIES | FRC/OFF/342/VOL:1 | RB306 |  | Appropriation | 22020306 | PRINTING OF SECURITY DOCUMENT | Recurrent |  | 10,000,000.00 | NGN | 10,000,000.00 | [6 empty] | Goods | Schedule of Delivery | Repeat Procurement | Lowest Evaluated Responsive Bid | Accounting Officer-Permanent Secretary | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-11 | 2024-06-18 | 0 | 2024-01-03 | 2024-01-09 | No | 2024-01-14 | 2024-01-27 | 2024-01-27 | 2024-02-11 | 2024-02-15 | 2024-02-17 | 2024-03-03 | 2024-04-13 | 2024-04-13 | 2024-04-15 | 2024-04-21 | 2024-04-27 | 2024-05-01 | 2024-05-07 | 2024-05-20 | 2024-05-27 | 2024-06-04 | 2024-06-25 | 2024-07-03 | 2024-07-10 | 2024-10-07 | 2024-10-08 |  |  |  | '' |  |  |  | ''
29 | ocds-gyl66f-539001007-000063 | UNIFORMS & OTHER DOCUMENTS | FOR PRODUCTIVITY | FRC/OFF/445/VOL:1 | RB309 |  | Appropriation | 22020309 | UNIFORMS & OTHER DOCUMENTS | Recurrent |  | 1,100,000.00 | NGN | 1,100,000.00 | [6 empty] | Goods | Schedule of Delivery | Repeat Procurement | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-13 | 2024-06-20 | 0 | 2024-01-02 | 2024-01-08 |  | 2024-01-13 | 2024-01-26 | 2024-01-26 | 2024-02-10 | 2024-02-14 | 2024-02-16 | 2024-03-02 | 2024-04-12 | 2024-04-12 | 2024-04-14 | 2024-04-20 | 2024-04-26 | 2024-04-30 | 2024-05-06 | 2024-05-19 | 2024-05-27 | 2024-06-06 | 2024-06-27 | 2024-06-28 | 2024-07-05 | 2024-10-02 | 2024-10-03 |  |  |  | '' |  |  |  | ''
30 | ocds-gyl66f-539001007-000064 | MAINTENANCE OF MOTOR VEHICLE/ TRANSPORT EQUIPMENT | FOR SMOOTH WORKING ACTIVITIES | FRC/OFF/411/VOL:1 | RC401 |  | Appropriation | 22020401 | MAINTENANCE OF MOTOR VEHICLE/ TRANSPORT EQUIPMENT | Recurrent |  | 7,000,000.00 | NGN | 7,000,000.00 | [6 empty] | Non-Consultancy Services | Lump Sum | Repeat Procurement | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-01-03 | 2024-01-09 | -1 | 2024-01-14 | 2024-01-27 | 2024-01-27 | 2024-02-11 | 2024-02-15 | 2024-02-21 | 2024-02-23 | 2024-02-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 | 2024-04-11 | 2024-04-17 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-18 | 2024-05-20 | No | 2024-05-31 | 2024-06-04 | 2024-06-10 | 2024-06-23 |  | 2024-06-11 | 2024-08-05 | 2024-06-25 | 2024-06-18 | 2024-06-25 | 366 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
31 | ocds-gyl66f-539001007-000065 | MAINTENANCE OF OFFICE FURNITURE | FOR SMOOTH WORKING ENVIRONMENT | FRC/OFF/346/VOL:1 | RC402 |  | Appropriation | 22020402 | MAINTENANCE OF OFFICE FURNITURE | Recurrent |  | 3,964,728.00 | NGN | 3,964,728.00 | [6 empty] | Goods | Schedule of Delivery | Direct Labour | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-13 | 2024-06-20 | 0 | 2024-01-04 | 2024-01-10 | No | 2024-01-15 | 2024-01-28 | 2024-01-28 | 2024-02-12 | 2024-02-16 | 2024-02-18 | 2024-03-04 | 2024-04-14 | 2024-04-14 | 2024-04-16 | 2024-04-22 | 2024-04-28 | 2024-05-02 | 2024-05-08 | 2024-05-21 | 2024-05-28 | 2024-06-05 | 2024-06-27 | 2024-06-28 | 2024-07-10 | 2024-10-07 | 2024-10-08 |  |  |  | '' |  |  |  | ''
32 | ocds-gyl66f-539001007-000066 | MAINTENANCE OF OFFICE BUILDING/RESIDENTIAL QTRS | FOR SMOOTH WORKING ACTIVITIES | FRC/OFF/242/VOL:1 | RC402 |  | Appropriation | 22020403 | MAINTENANCE OF OFFICE BUILDING/RESIDENTIAL QTRS | Recurrent |  | 5,220,211.00 | NGN | 5,220,211.00 | [6 empty] | Works | BOQ | Request for Quotation | Lowest Evaluated Responsive Bid | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-11 | 2024-06-18 | 0 | 2024-01-02 | 2024-01-08 | No | 2024-01-13 | 2024-01-26 | 2024-01-26 | 2024-02-10 | 2024-02-14 | 2024-02-16 | 2024-03-02 | 2024-04-12 | 2024-04-12 | 2024-04-14 | 2024-04-20 | 2024-04-26 | 2024-04-30 | 2024-05-06 | 2024-05-19 | 2024-05-26 | 2024-06-04 | 2024-06-25 | 2024-06-26 | 2024-07-09 | 2024-10-06 | 2024-10-07 |  |  |  | '' |  |  |  | ''
33 | ocds-gyl66f-539001007-000067 | MAINTENANCE OF OFFICE/ IT EQUIPMENT | FOR SMOOTH RUNNING ACTIVITIES | FRC/OFF/298/VOL:1 | RC404 |  | Appropriation | 22829404 | MAINTENANCE OF OFFICE/IT EQUIPMENT | Recurrent | NGN | 4,492,410.00 | NGN | 4,492,410.00 | [6 empty] | Non-Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-01-03 | 2024-01-09 | -1 | 2024-01-14 | 2024-01-27 | 2024-01-27 | 2024-02-11 | 2024-02-15 | 2024-02-21 | 2024-02-23 | 2024-02-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 | 2024-04-11 | 2024-04-17 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-18 | 2024-05-20 | Yes | 2024-05-31 | 2024-06-04 | 2024-06-10 | 2024-06-23 |  | 2024-06-25 | 2024-07-30 | 2024-07-09 | 2024-07-02 | 2024-07-09 | 300 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
34 | ocds-gyl66f-539001007-000068 | MAINTENANCE OF PLANTS/ GENERATORS | FOR SMOOTH RUNNING OF OFFICE | FRC/OFF/401/VOL:1 | RC405 |  | Appropriation | 22020405 | MAINTENANCE OF PLANTS/ GENERATORS | Recurrent | NGN | 5,000,000.00 | NGN | 5,000,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-01-04 | 2024-01-10 | -1 | 2024-01-15 | 2024-01-28 | 2024-01-28 | 2024-02-12 | 2024-02-16 | 2024-02-22 | 2024-02-24 | 2024-02-26 | 2024-03-12 | 2024-04-10 | 2024-04-10 | 2024-04-12 | 2024-04-18 | 2024-05-03 | 2024-05-05 | 2024-05-11 | 2024-05-19 | 2024-05-21 | Yes | 2024-06-01 | 2024-06-05 | 2024-06-11 | 2024-06-24 |  | 2024-06-24 | 2024-05-22 | 2024-07-09 | 2024-07-02 | 2024-07-09 | 360 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
35 | ocds-gyl66f-539001007-000069 | OTHER MAINTENANCE SERVICES | FOR SMOOTH RUNNING OF OFFICE | FRC/OFF/516/VOL:1 | RC406 |  | Appropriation | 22020406 | OTHER MAINTENANCE SERVICES | Recurrent | NGN | 20,608,530.00 | NGN | 20,608,530.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-08 | 2024-01-14 | 2 | 2024-01-19 | 2024-02-01 | 2024-02-01 | 2024-02-16 | 2024-02-20 | 2024-02-26 | 2024-02-28 | 2024-03-01 | 2024-03-16 | 2024-04-14 | 2024-04-14 | 2024-04-16 | 2024-04-22 | 2024-05-07 | 2024-05-09 | 2024-05-15 | 2024-05-23 | 2024-05-25 | Yes | 2024-06-05 | 2024-06-09 | 2024-06-15 | 2024-06-28 |  | 2024-06-26 | 2024-07-17 | 2024-07-10 | 2024-07-03 | 2024-07-10 | 360 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
36 | ocds-gyl66f-539001007-000070 | LOCAL TRAINING | FOR HUMAN CAPITAL DEVELOPMENT | FRC/OFF/249/VOL:1 | RD501 |  | Appropriation | 22020501 | LOCAL TRAINING | Recurrent | NGN | 35,000,000.00 | NGN | 35,000,000.00 | [6 empty] | Consultancy Services | Time Based | Selective Tendering | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-02-05 | 2024-02-11 | 2 | 2024-02-16 | 2024-02-29 | 2024-02-29 | 2024-03-15 | 2024-03-19 | 2024-03-25 | 2024-03-27 | 2024-03-29 | 2024-04-13 | 2024-05-12 | 2024-05-12 | 2024-07-03 | 2024-05-20 | 2024-06-04 | 2024-06-06 | 2024-06-12 | 2024-06-20 | 2024-06-22 | Yes | 2024-07-03 | 2024-07-07 | 2024-07-13 | 2024-07-26 |  | 2024-08-05 | 2024-09-03 | 2024-08-22 | 2024-08-15 | 2024-08-22 | 7 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
37 | ocds-gyl66f-539001007-000071 | INTERNATIONAL TRAINING | FOR HUMAN CAPITAL DEVELOPMENT | FRC/OFF/451/VOL:1 | RD502 |  | Appropriation | 22020502 | INTERNATIONAL TRAINING | Recurrent | NGN | 34,000,000.00 | NGN | 34,000,000.00 | [6 empty] | Consultancy Services | Time Based | Selective Tendering | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-09 | 2024-01-15 | 2 | 2024-01-20 | 2024-02-02 | 2024-02-02 | 2024-02-17 | 2024-02-21 | 2024-02-27 | 2024-02-29 | 2024-03-02 | 2024-03-17 | 2024-04-15 | 2024-04-15 | 2024-04-17 | 2024-04-23 | 2024-05-08 | 2024-05-10 | 2024-05-16 | 2024-05-24 | 2024-05-26 | Yes | 2024-06-06 | 2024-06-10 | 2024-06-16 | 2024-06-29 |  | 2024-06-24 | 2024-07-19 | 2024-07-12 | 2024-07-05 | 2024-07-12 | 7 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
38 | ocds-gyl66f-539001007-000072 | SECURITY CHARGES | TO SECURE THE OFFICE | FRC/OFF/367/VOL:1 | RE601 |  | Appropriation | 22020601 | SECURITY CHARGES | Recurrent |  | 24,500,000.00 | NGN | 24,500,000.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-10 | 2024-01-16 | -1 | 2024-01-21 | 2024-02-03 | 2024-02-03 | 2024-02-18 | 2024-02-22 | 2024-02-28 | 2024-03-01 | 2024-03-03 | 2024-03-18 | 2024-04-16 | 2024-04-16 | 2024-04-18 | 2024-04-24 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-05-25 | 2024-05-27 | Yes | 2024-06-07 | 2024-06-11 | 2024-06-17 | 2024-06-30 |  | 2024-07-02 | 2024-07-23 | 2024-07-16 | 2024-07-09 | 2024-07-16 | 360 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
39 | ocds-gyl66f-539001007-000073 | LAND USE CHARGES | FOR OFFICE USE | FRC/OFF/71/VOL:1 | RE602 |  | Appropriation | 22020602 | LAND USE CHARGES | Recurrent | NGN | 24,000,000.00 | NGN | 24,000,000.00 | [6 empty] | Non-Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-02-01 | 2024-02-07 | 2 | 2024-02-12 | 2024-02-25 | 2024-02-25 | 2024-03-11 | 2024-03-15 | 2024-03-21 | 2024-03-23 | 2024-03-25 | 2024-04-09 | 2024-05-08 | 2024-05-08 | 2024-05-10 | 2024-05-16 | 2024-05-31 | 2024-06-02 | 2024-06-08 | 2024-06-16 | 2024-06-18 | Yes | 2024-06-29 | 2024-07-03 | 2024-07-09 | 2024-07-22 |  | 2024-07-15 | 2024-08-06 | 2024-07-30 | 2024-07-22 | 2024-07-30 | 360 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
40 | ocds-gyl66f-539001007-000074 | CLEANING AND FUMIGATION SERVICES | FOR CONDUCIVE ENVIRONMENT | FRC/OFF/366/VOL:1 | RE606 |  | Appropriation | 22020606 | CLEANING AND FUMIGATION SERVICES | Recurrent | NGN | 28,298,868.00 | NGN | 28,298,868.00 | [6 empty] | Consultancy Services | Time Based | Selective Tendering | Least Cost Selection(LCS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-11 | 2024-01-17 | 2 | 2024-01-22 | 2024-02-04 | 2024-02-04 | 2024-02-19 | 2024-02-23 | 2024-02-29 | 2024-03-02 | 2024-03-04 | 2024-03-19 | 2024-04-17 | 2024-04-17 | 2024-04-19 | 2024-04-25 | 2024-05-10 | 2024-05-12 | 2024-05-18 | 2024-05-26 | 2024-05-28 | Yes | 2024-06-08 | 2024-06-12 | 2024-06-18 | 2024-07-01 |  | 2024-07-01 | 2024-08-13 | 2024-07-30 | 2024-07-15 | 2024-07-30 | 14 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
41 | ocds-gyl66f-539001007-000075 | FINANCIAL CONSULTING | FOR ACCOUNTABILITY | FRC/OFF/805/VOL:1 | RF701 |  | Appropriation | 22020701 | FINANCIAL CONSULTING | Recurrent | NGN | 9,100,317.00 | NGN | 9,100,317.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-02-02 | 2024-02-08 | 2 | 2024-02-13 | 2024-02-26 | 2024-02-26 | 2024-03-12 | 2024-03-16 | 2024-03-22 | 2024-03-24 | 2024-03-26 | 2024-04-10 | 2024-05-09 | 2024-05-09 | 2024-05-11 | 2024-05-17 | 2024-06-01 | 2024-06-03 | 2024-06-09 | 2024-06-17 | 2024-06-19 | Yes | 2024-06-30 | 2024-07-04 | 2024-07-10 | 2024-07-23 |  | 2024-07-11 | 2024-08-05 | 2024-07-25 | 2024-07-18 | 2024-07-25 | 14 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
42 | ocds-gyl66f-539001007-000076 | INFORMATION TECHNOLOGY CONSULTING | FOR EFFECTIVE OFFICE USE | DPRS/FRC/411 | RF702 |  | Appropriation | 22020702 | INFORMATION TECHNOLOGY CONSULTING | Recurrent | NGN | 2,800,698.00 | NGN | 2,800,698.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-02-01 | 2024-02-07 | 2 | 2024-02-12 | 2024-02-25 | 2024-02-25 | 2024-03-11 | 2024-03-15 | 2024-03-21 | 2024-03-23 | 2024-03-25 | 2024-04-09 | 2024-05-08 | 2024-05-08 | 2024-05-10 | 2024-05-16 | 2024-05-31 | 2024-06-02 | 2024-06-08 | 2024-06-16 | 2024-06-18 | Yes | 2024-06-29 | 2024-07-03 | 2024-07-09 | 2024-07-22 |  | 2024-07-16 | 2024-08-07 | 2024-07-30 | 2024-07-23 | 2024-07-30 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
43 | ocds-gyl66f-539001007-000077 | LEGAL SERVICES | FOR LEGAL WORKS | FRC/OFF/156/VOL:1 | RF703 |  | Appropriation | 22020703 | LEGAL SERVICES | Recurrent |  | 30,000,000.00 | NGN | 30,000,000.00 | [6 empty] | Consultancy Services | Time Based | Request for Quotation | Fixed Budget Selection (FBS) | Parastatal Tenders Board | Post-Qualification | Post-Review | 2024-01-04 | 2024-01-10 | 2 | 2024-01-15 | 2024-01-28 | 2024-01-28 | 2024-02-12 | 2024-02-16 | 2024-02-22 | 2024-02-24 | 2024-02-26 | 2024-03-12 | 2024-04-10 | 2024-04-10 | 2024-04-12 | 2024-04-18 | 2024-05-03 | 2024-05-05 | 2024-05-11 | 2024-05-19 | 2024-05-21 | Yes | 2024-06-01 | 2024-06-05 | 2024-06-11 | 2024-06-24 |  | 2024-06-17 | 2024-07-15 | 2024-07-01 | 2024-06-24 | 2024-07-01 | 60 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
44 | ocds-gyl66f-539001007-000078 | MEDICAL CONSULTING | FOR MEDICAL TREATMENT | FRC/OFF/329/VOL:1 | RF708 |  | Appropriation | 22020708 | MEDICAL CONSULTING | Recurrent | NGN | 7,000,000.00 | NGN | 7,000,000.00 | [6 empty] | Consultancy Services | Lump Sum | Emergency | Least Cost Selection(LCS) | Accounting Officer-Director-General/CEO | Post-Qualification | Post-Review | 2024-01-03 | 2024-01-09 | 2 | 2024-01-14 | 2024-01-27 | 2024-01-27 | 2024-02-11 | 2024-02-15 | 2024-02-21 | 2024-02-23 | 2024-02-25 | 2024-03-11 | 2024-04-09 | 2024-04-09 | 2024-04-11 | 2024-04-17 | 2024-05-02 | 2024-05-04 | 2024-05-10 | 2024-05-18 | 2024-05-20 | Yes | 2024-05-31 | 2024-06-04 | 2024-06-10 | 2024-06-23 |  | 2024-06-12 | 2024-07-04 | 2024-06-27 | 2024-06-20 | 2024-06-27 | 30 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  |  |  | '' |  |  |  | ''
45 | ocds-gyl66f-539001007-000079 | MOTOR VEHICLE FUEL COST | FOR VEHICLES MOVEMENT | FRC/OFF/240/VOL:1 | RG801 |  | Appropriation | 22020801 | MOTOR VEHICLE FUEL COST | Recurrent | NGN | 24,000,000.00 | NGN | 24,000,000.00 | [6 empty] | Goods | Rates/% | Request for Quotation | Lowest Evaluated Responsive Bid | Parastatal Tenders Board | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-17 | 2024-06-24 | 0 | 2024-01-02 | 2024-01-08 | No | 2024-01-13 | 2024-01-26 | 2024-01-26 | 2024-02-10 | 2024-02-14 | 2024-02-16 | 2024-03-02 | 2024-04-12 | 2024-04-12 | 2024-04-14 | 2024-04-20 | 2024-04-26 | 2024-04-30 | 2024-05-06 | 2024-05-19 | 2024-06-03 | 2024-06-10 | 2024-07-03 | 2024-07-04 | 2024-07-11 | 2024-10-08 | 2024-10-09 |  |  |  | '' |  |  |  | ''
46 | ocds-gyl66f-539001007-000080 | PLANT/GENERATOR FUEL COST | FOR SMOOTH RUNNING OF THE GENERATOR | FRC/OFF/337/VOL:1 | RG803 |  | Appropriation | 22020803 | PLANT/GENERATOR FUEL COST | Recurrent |  | 15,000,000.00 | NGN | 15,000,000.00 | [6 empty] | Goods | Schedule of Delivery | Request for Quotation | Lowest Evaluated Responsive Bid | Accounting Officer-Permanent Secretary | Post-Qualification | Post-Review | 2001-01-01 | 2001-01-01 | -1 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2001-01-01 |  | 2001-01-01 | 2001-01-01 | 2001-01-01 | 2024-06-13 | 2024-06-20 | 0 | 2024-01-01 | 2024-01-07 | No | 2024-01-12 | 2024-01-25 | 2024-01-25 | 2024-02-09 | 2024-02-13 | 2024-02-15 | 2024-03-01 | 2024-04-11 | 2024-04-11 | 2024-04-13 | 2024-04-19 | 2024-04-25 | 2024-04-29 | 2024-05-05 | 2024-05-18 | 2024-05-27 | 2024-06-06 | 2024-07-01 | 2024-07-08 | 2024-07-22 | 2024-10-19 | 2024-10-20 |  |  |  | '' |  |  |  | ''

## Records
NOCOPO DATA
AWARD RECORD
MDA
S/N | Tender ID | Planning | Tender Title | Tender Description | Tender Status | Actual Procurement Method | Procurement Method Rationale | Actual Selection Method | Actual Approval Authority | Submission Method | Submission method details | Actual Tendering Period Start Date | Actual Tendering Period End Date | Advertisement Media | Any Enquiries | Eligibility Criteria | Actual Bid Opening | Number of Tenderers | Names of Tenders | Actual Bid Evaluation Period Start Date | Actual Bid Evaluation Period End Date | Actual Procuring Entity Evaluation Approval Start Date | Actual Procuring Entity Evaluation Approval End Date | Certificate Of No Objection Start Date | Certificate Of No Objection End Date | Certificate Of Not Applicable | Project Code | Award Title | Award Description | Award Status | Award Date | Tender | Contractor Awarded Name | BPP Number | To lowest priced tenderer | Justification for award | Contract Currency | Contract Value | Project Code | Contract Title | Contract Description | Contract Status | Award | Date Contract Signed | Actual Contract Period Start Day | Actual Contract Period End Day | Project Code | Contract | Date of Evaluation | AP Curency | Amount Paid as at Date | Project Status | Percentage Completion | Final Cost Curency | Final Cost | Any Contract Variation | Variation Amount Currency | Variation Amount | BPP Ref No for Approval of Variation | Currency | Total Revised Estimated Contract Amount
RptRow | Tender_ID | Planning_FK_Item | Tender_Title | Tender_Description | Tender_Status_FK_Item | Actual_Procurement_Method_FK_Item | Procurement_Method_Rationale | Actual_Selection_Method_FK_Item | Actual_Approval_Authority_FK_Item | Submission_Method_FK_Item | Submission_method_details | Actual_Tendering_Period_Start_Date__FEx | Actual_Tendering_Period_End_Date_FEx | Advertisement_Media | Any_Enquiries_Item | Eligibility_Criteria | Actual_Bid_Opening_FEx | Number_of_Tenderers | Names_of_Tenders | Actual_Bid_Evaluation_Period_Start_Date_FEx | Actual_Bid_Evaluation_Period_End_Date_FEx | Actual_Procuring_Entity_Evaluation_Approval_Start_Date_FEx | Actual_Procuring_Entity_Evaluation_Approval_End_Date_FEx | Certificate_Of_No_Objection_Start_Date_FEx | Certificate_Of_No_Objection_End_Date_FEx | Certificate_Of_Not_Applicable_Item | Award_ID | Award_Title | Award_Description | Award_Status_FK_Item | Award_Date_FEx | Tender_FK_Item | Contractor_Awarded_Name | BPP_Number | To_lowest_priced_tenderer_FK_Item | Justification_for_award | Contract_Currency_FK_Item | Contract_Value_F | Contract_ID | Contract_Title | Contract_Description | Contract_Status_FK_Item | Award_FK_Item | Date_Contract_Signed_FEx | Actual_Contract_Period_Start_Day_FEx | Actual_Contract_Period_End_Day_FEx | Implementation_ID | Contract_FK_Item | Date_of_Evaluation_FEx | AP_Curency_FK_Item | Amount_Paid_as_at_Date_F | Project_Status_as_at_date_FK_Item | Percentage_Completion_as_at_date | Final_Cost_Curency_FK_Item | Final_Cost_F | Any_Contract_Variation_FK_Item | V_Amount_Currency_FK_Item | Variation_Amount_F | BPP_Ref_No_for_Approval_of_Variation | TREC_Amount_Currency_FK_Item | Total_Revised_Estimated_Contract_Amount_F